## Risk Register
Risks |  |  | Baseline Risk Level |  |  | Response |  | Post-mitigation Risk Level |  |  | Output | Review
Risk ID | Cause | Effect | Likelihood | Severity | Overall Risk Level | Strategy | Mitigation | Likelihood | Severity | Overall Risk Level
1 | Poor risk management | Unchecked risks may have significant impact without prior plan for mitigation or protocol for resolution. | 5 | 5 | 25 | Reduce | Utilization of a comprehensive risk management strategy to identify, assess, plan for and manage risks associated with or agnostic of the project. | 1 | 1 | 1 | Strategic assessment of risks drastically reduces likelihood of unforseen complications, especially those that are severe. | TBC ~ 26th June
2 | Deliverables not fully described | Ineffective decription of deliverables could lead to delivery of sub-standard product on conclusion of the project. | 3 | 4 | 12 | Reduce | Conduct extensive requirements and information gathering to determine, in detail, the deliverables required. | 1 | 4 | 4 | Gathering of detailed project information will elucidate project deliverables and drastically reduce risk. | TBC ~ 26th June
3 | Lack of clear objectives | Clear objectives are necessary in guidance of a successful project. | 3 | 3 | 9 | Reduce | Detailed objectives will be included in requirements gathering. | 1 | 3 | 3 | Requirements gathering will ensure clear objectives. | TBC ~ 26th June
4 | Ineffective Project Plan | An ineffective project plan would not provide sufficient structure to carry out a successful project | 3 | 4 | 12 | Reduce | An effective project plan is highly important and therefore significant time will be spent planning before execution. | 1 | 2 | 2 | Plenty of time spent planning the project in detail reduces the likelihood of a poor plan. | TBC ~ 26th June
5 | Failure to meet final Project Deadline | Many reasons could contribute (illness, absence, etc.) but failing to deliver the project on time would be a drastic negative result for the project. | 3 | 5 | 15 | Reduce | Good project planning (incl. buffer days, burndown charts, intermediary deadlines, etc.) will reduce the likelihood of missing the final project deadline. | 1 | 5 | 5 | A good plan and consistent review of progress will minimize risk of unforseen delays and failure to deliver on time. | TBC ~ 26th June
6 | Product fails to meet desired requirements | Final deliverables which are not to the required standard set out in the brief would constitute a project failure or at least demonstrate poor execution. | 4 | 5 | 20 | Reduce | Care will be taken to ensure that the Minimum Viable Product (MVP) is produced before enhancing the work standard or working on extension tasks. | 2 | 3 | 6 | Whilst the MVP is below the desired quality, it's the required standard and must be reached well in advance of final delivery. | TBC ~ 26th June
7 | Illness or other unforseen absence | Illness/ unforseen absence would reduce available time to work on the project and would contribute to project delays. | 3 | 3 | 9 | Reduce | Whilst this risk cannot be easily predicted, good planning (e.g. by incorporating buffer time in work schedule) will allow for minor delays. | 3 | 1 | 3 | The likelihood of unforseen absence is hard to reduce but the impact can be mitigated by good planning. | TBC ~ 26th June
8 | Poor Communication | Poor communication between colleagues or with a client may create problems around the project. | 2 | 4 | 8 | Accept | This is an individual project but communication with the client must be prompt, clear and professional. | 2 | 4 | 8 | Maintaining professional standards when communicating is always necessary. | TBC ~ 26th June
9 | Data Loss | Catastrophic data loss is always a distinct possibility and could involve losing a completed deliverable. | 2 | 5 | 10 | Reduce | Frequent back ups and good version control will reduce the impact of data loss or corruption. | 2 | 2 | 4 | A simple fix to a dangerous risk - ensure that GitHub project repo is actively maintined. | TBC ~ 26th June
10 | Poor Change Management | Ineffectively maintaining Version Control Management could lead to data loss or persistent errors. | 3 | 4 | 12 | Reduce | Using GitHub to actively manage project version control and pushing work to the repository once a week or more. | 2 | 2 | 4 | Using an effective version control tool to reduce chances for poor change management. | TBC ~ 26th June
11 | Sensitive Customer Information | Handling sensitive customer information poses GDPR risks and must be taken incredibly seriously. | 5 | 5 | 25 | Avoid | Fake customer test data will be used to avoid handling real customer information, nonetheless, security will be considered. | 1 | 5 | 5 | Avoiding handling real customer data mitigates the accompanying risk but security is still important. | TBC ~ 26th June
12 | Insufficient Testing Coverage | Ineffective testing risks exposure to bugs or other underlying risks in the system going undiscovered. | 3 | 5 | 15 | Reduce | Set up comprehensive testing in line with brief and deliverables and ensure that the system passes tests before delivery. | 1 | 3 | 3 | Designing testing alongside the system (TDD) to minimize chance of ineffective tests. | TBC ~ 26th June
13 | Lots of Computer Working | Long periods spent working at a computer can cause health issues such as RSI or vision problems. | 3 | 3 | 9 | Reduce | Using proper equipment and taking short, frequent breaks to move about will minimize the associated health risks | 1 | 3 | 3 | Being wary of the health risks of computer working and taking steps to avoid them. | TBC ~ 26th June

## Risk Matrix
Severity | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
Likelihood